## Sheet1
USER STORY | TASKS | ESTIMATED EFFORT | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7
As a consumer, I will be able to view the page’s contents in a non confusing manner by scrolling and looking at the page in an organized form. | 1. Design Home and Shop Page Structure 2. Code the Home and Shop Page Structure based off of the design. 3. Test Code. 4. Take to Product Owner for review | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
As a consumer, I will be able to navigate my way throughout the website with a horizontal navigation bar. | 1. Design the horizontal navigation bar. 2. Code the horizontal navigation bar. 3. Test Code. 4. Take to Product Owner for review | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
As a consumer, I will be able to find and click on social media links which will take me to the company's social media. | 1. Code Social Media links into the bottom of the Page Structure. 2. Test Code. 3. Take to Product Owner for review | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
As a consumer, I will be able to find the company’s contact information on this page with relative ease. | 1. Code Company’s Contact Information Structure's designated area for projects. 2. Test Code. 3. Take to Product Owner for review | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
As a consumer, I will be able to send the company an email by inputting contents within a form’s fields such as name, email, subject, and message, and then clicking a submit button. | 1. Code form with field's such as name, email, subject, and message, and a submit button into the page 2. Test Code. 3. Take to Product Owner for review | 15 | 0 | 0 | 10 | 5 | 0 | 0 | 0
As a consumer, I will be able to learn about the staff and CEO of the company through information and an image of what they look like. | 1. Code information on the CEO and staff and add images of what they look like 2. Test Code. 3. Take to Product Owner for review | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0