## Sheet1
USER STORY | TASKS | ESTIMATED EFFORT | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7
As a consumer, I will be able to view the page’s contents in a non confusing manner by scrolling and looking at the page in an organized form. | 1. Design Home and Shop Page Structure 2. Code the Home and Shop Page Structure based off of the design. 3. Test Code. 4. Take to Product Owner for review | 20 | 5 | 10 | 5 | 0 | 0 | 0 | 0
As a consumer, I will be able to navigate my way throughout the website with a horizontal navigation bar. | 1. Design the horizontal navigation bar. 2. Code the horizontal navigation bar. 3. Test Code. 4. Take to Product Owner for review | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0
As a consumer, I will be able to find and click on social media links which will take me to the company's social media. | 1. Code Social Media links into the bottom of the Page Structure. 2. Test Code. 3. Take to Product Owner for review | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0
As a consumer, I will be able to view and understand the company’s previous projects through images and descriptions to be able to gain insight on the company’s work. | 1. Code Projects into the Home Page Structure's designated area for projects. 2. Test Code. 3. Take to Product Owner for review | 5 | 0 | 0 | 0 | 3 | 2 | 0 | 0
As a consumer, I will be able to view the products that the company’s selling and be able to view the price of such products. | 1. Code Products into the Shop Page Structure's designated area for Products. 2. Test Code. 3. Take to Product Owner for review | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 2